## Gantt Chart
Project PONDER Gantt Chart | [7 empty] | October |  | November | [5 empty] | December |  |  |  |  | January
TASK NO. | TASK TITLE | RISK LEVEL | TASK OWNER | START DATE | DUE DATE | DURATION / DAYS | % OF TASK COMPLETE | PHASE ONE |  |  |  | PHASE TWO |  |  | PHASE THREE |  |  |  | PHASE FOUR |  |  |  | PHASE FIVE
[8 empty] | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18
0 | Deadlines / Labs
0.1 | Design Brief Submission | HIGH | All | N/A | 27-10-2020 | N/A | 100%
0.2 | Project Report Submission | HIGH | All | N/A | 2021-01-05 | N/A | 100%
0.3 | Project Presentation | HIGH | All | N/A | 25-01-2021 | N/A | 0%
0.4.1 | Lab 1 - 10AM-1PM - 16AB04 | LOW | Hardware | 2020-05-11 | N/A | 3 hours | 100%
0.4.2 | Lab 2 - 10AM-1PM - 16AB04 | LOW | Hardware | 19-11-2020 | N/A | 3 hours | 100%
0.4.3 | Lab 3 - 10AM-1PM - 16AB04 | LOW | Hardware | 2020-03-12 | N/A | 3 hours | 100%
0.4.4 | Extra Lab - 10AM-1PM - 16AB04 | LOW | Hardware | 2020-10-12 | N/A | 3 hours | 100%
1 | Research
1.1.1 | Water Pollutant Research | LOW | All | 2020-10-19 | 2020-10-21 | 3 | 100%
1.1.2 | Sensor Choices | MEDIUM | All | 2020-10-19 | 2020-10-21 | 3 | 100%
2 | Design - Hardware
2.1 | Solar Power Calculation | LOW | Hardware | 2020-10-21 | 2020-10-24 | 4 | 100%
2.2 | Component Choices | LOW | Hardware | 2020-10-21 | 2020-10-24 | 4 | 100%
2.3 | Hardware Block Diagram | LOW | Hardware | 2020-10-21 | 2020-10-24 | 4 | 100%
2.4 | Ordering Components | MEDIUM | Hardware | 2020-10-25 | 2020-11-20 | 26 | 100%
2.5.1 | Enclosure Design Ideas | LOW | Hardware | 2020-10-21 | 2020-11-14 | 24 | 100%
2.5.2 | Enclosure Build | LOW | Hardware | 2020-11-01 | 2020-12-03 | 33 | 100%
2.6 | Arduino Firmware | MEDIUM | Hardware | 2020-11-01 | 2020-12-10 | 40 | 100%
2.7 | PCB/Veroboard Design & Build | MEDIUM | Hardware | 2020-11-15 | 2021-01-02 | 48 | 100%
2.8 | Software Integration | MEDIUM | Hardware | 2020-12-02 | 2021-01-02 | 31 | 100%
3 | Design - Software
3.1.1 | Basic Visual Design of the App | LOW | Software | 2020-10-19 | 2020-10-26 | 8 | 100%
3.1.2 | Building App | MEDIUM | Software | 2020-10-26 | 2020-12-10 | 45 | 100%
3.2 | Software Block Diagram | LOW | Software | 2020-10-19 | 2020-10-26 | 8 | 100%
3.3 | DB Server Setup | MEDIUM | Software | 2020-10-27 | 2020-11-04 | 8 | 100%
3.4 | Research Bluetooth Data Transmission | MEDIUM | Software | 2020-11-02 | 2020-12-10 | 39 | 100%
3.5 | Research GSM/GPRS/GPS Data Transmission | HIGH | Software | 2020-11-02 | 2020-12-10 | 39 | 100%
3.6 | Implement Data Communication | HIGH | Software | 2020-11-23 | 2021-02-01 | 69 | 100%
4 | Documentation
4.1 | Specification Verification Matrix | LOW | All | 2020-10-21 | 2020-10-27 | 7 | 100%
4.2 | SAGE, EIA, DMP forms | LOW | All | 2020-10-21 | 2020-10-27 | 7 | 100%
4.3 | Risk Assessment Matrix | LOW | All | 2020-10-21 | 2020-10-27 | 7 | 100%
4.4 | Project Report | LOW | All | 2020-12-11 | 2021-01-05 | 25 | 100%
4.5 | Project Presentation | LOW | All | 2021-01-05 | 2021-01-25 | 21 | 0%

## Task Descriptions
Task No. | Task Title | Description | Est. Time Req. | Task Owner | Additional Notes | Risks | Probability | Impact | Risk Level
1 | Research
1.1.1 | Water Pollutant Research | Each team member is assigned a type of water pollution to research and write a short document on. Research should include information on the source, effects, and ways to measure the type of pollution. | 3 days | 1) Vasily 2) Jordan 3) Kieran 4) Lawrie 5) Mark 6) Pranay 7) Priyam 8) Robby | 1) Ammonia 2) Fertilizers such as nitrates and phosphates 3) Detergents and surfactants 4) Oils and hydrocarbons 5) Organic and other solvents 6) Heavy metals such as cadmium, mercury, lead and arsenic 7) Oxygen-depleting substances 8) Sulphur Dioxide | Risk of inaccurate, outdated, or inapplicable information, among others. Minimize risk by referencing relevant and reputable sources. Ensure that information presented is relevant and up to date. | Rare | Very Low | LOW
1.1.2 | Sensor Choices | Use Water Pollutant Research to inform choice of sensor to be used in our project. Requires consideration of multiple factors, including how useful the sensor data is, price of sensor, size/weight/form factor constraints, voltage required, analogue/digital pin requirements, ease of integration, ease of acquirement, etc. | 3 days | All | Prerequisite to further tasks concerning component selection. | Risk of choice of sensors which later turn out to be incompatible, less robust, inprecise, useless, difficult to integrate, etc. Minimize risk by choosing sensors from reputable vendor with documentation/data sheets available. Check voltage and pin requirements thoroughly. | Unlikely | High | MEDIUM
2 | Design - Hardware
2.1 | Solar Power Calculation | Calculate size of solar panel needed and size of battery needed, taking into account solar irradiance on a horizontal surface in December, and various charging inefficiencies. | 4 days | Mark | Must be completed in order to inform choices of components, including: size/number of batteries, size of solar panel, type of battery charger, type of microcontroller, etc | Many of the calculations depend on assumptions. There is a risk that real world use will differ from calculations as a result. For example, we assume that the Arduino NANO consumes 20mA in Idle mode, but this does not include idle current draw from other sensors. However, the NANO can be put into deep sleep mode, reducing current draw substantially. | Rare | Low | LOW
2.2 | Component Choices | Make decisions concerning what components to buy, and from what vendors. Consider the price of components, and ensure compatibility between them. | 4 days | Mark | The Bluetooth and GSM/GPRS/GPS modules both use UART. Need to choose on or the other. pH probe may be unsuitable for extended immersion | Risk of unforseen compatibility issues between components. Minimise risk by reading data sheets and checking pin and voltage requirements. | Rare | Medium | LOW
2.3 | Hardware Block Diagram | Create system overview block diagram, showing top level representation of hardware modules and how they interface with each other | 4 days | Mark, Lawrie |  | No risks involved. Diagram can always be modified to account for errors or changes in design. | Rare | Very Low | LOW
2.4 | Ordering Components | Ordering the components chosen from various vendors. | 26 days | Mark | Prerequisite to Arduino Prototyping task | Risk of defective/counterfeit products. Minimise risk by purchasing from trustworthy vendors where possible. | Rare | High | MEDIUM
2.5.1 | Enclosure Design Ideas | Brainstorm various ideas regarding the design of the product's enclosure, taking into consideration buoyancy, cost, rigidity, waterproofing, stability, etc | 24 days | All | Prerequisite to task 2.5.2 | Risk of producing poor idea with a design flaw. Mitigate by asking everyone to share ideas and comment on each other's ideas. | Rare | Medium | LOW
2.5.2 | Enclosure Build | Design of enclosure in a CAD program, and building of enclosure. | 33 days | Mark, Jordan |  | Some difficulty in ensuring that enclosure is well built and water proof. | Possible | Very Low | LOW
2.6 | Arduino Firmware | Writing and testing sketches for each component individually, then integrating them into a single design. Measure power draw and take steps to lower it. | 40 days | Mark |  | Risk of unforseen issues when writing Arduino sketches. Mitigate by assigning multiple people and plenty of time to sort out issues. | Possible | Low | MEDIUM
2.7 | PCB/Veroboard Design & Build | Design and build of PCB or veroboard to hold Arduino modules and supporting components. | 48 days | Mark, Vasily | Begins in latter stage of Arduino Prototyping. Need to account for shipping time if PCB route chosen. | Risk of mistake with PCB design, or of long shipping time delaying project. Mitigate by having veroboard as a backup option, and considering UK manufacturer if short on time. | Unlikely | Low | MEDIUM
2.8 | Software Integration | Integrating hardware and software. | 31 days | Lawrie |  | Risk of problems with integration, particularly in comms. Minimise risk by developing both Bluetooth and GSM/GPRS comms in case one doesn't work. | Unlikely | High | MEDIUM
3 | Design - Software
3.1.1 | Basic Visual Design of the App | Create mockup of visual interface (GUI) for mobile application, that the end user will see. | 8 days | Robby |  | No risk. At this stage, design is just a preliminary mockup to give a general idea. It is likely to change in the future. | Rare | Very Low | LOW
3.1.2 | Building App | Building mobile application with the ability to present the data from each sensor from multiple devices in a clear and visually pleasing manner. | 45 days | Robby |  | Risk that data is not presented coherently. Significant risk that data transmission functionality of app does not work with Bluetooth and/or GSM/GPRS. Minimise risk by allocating significant time and energy to task. | Possible | Medium | MEDIUM
3.2 | Software Block Diagram | Create block diagram representing top level view of software side of the project. | 8 days | Pranay, Priyam |  | No risk. Diagram can be changed at any time if design changes. | Rare | Very Low | LOW
3.3 | DB Server Setup | Setup of back-end database server | 8 days | Pranay, Priyam |  | Risk of unforseen issues with storage/formatting/retrieval of data in database. Minimise by considering back up options/redundancies. | Unlikely | Medium | MEDIUM
3.4 | Research Bluetooth Data Transmission | Research the use of Bluetooth to transfer data from the device to the mobile app or database. | 39 days | Pranay, Priyam | Research may inform choice of communication method to be implemented. | Research may turn up issues regarding compatibility or ease of implementation with regards to our project. | Possible | Medium | MEDIUM
3.5 | Research GSM/GPRS/GPS Data Transmission | Research the use of GSM/GPRS to transfer data from the device to the mobile app or database. | 39 days | Pranay, Priyam | Research may inform choice of communication method to be implemented. GSM/GPRS+GPS is preferred but more complex. | Research may turn up issues regarding compatibility or ease of implementation with regards to our project. Will need to consider data transmission in the case of poor signal, and cost of SIM card. | Probable | Medium | HIGH
3.6 | Implement Data Communication | Implementation of data transmission via Bluetooth or GSM/GPRS. Bluetooth is much easier but greatly limits remote function of device, whereas GSM/GPRS+GPS allows for extended remote use, and GPS positioning, but at the cost of greater complexity. | 69 days | Pranay, Priyam, Lawrie | Data communication of some form is a 'must have' feature. The use of a GSM/GPRS+GPS module would allow for remote use and GPS data which are 'should have' features, whereas Bluetooth communication would only satisfy the necessary 'must have' feature. | Risk that data communication via GSM/GPRS proves too difficult to implement. Minimise risk by having the option to implement Bluetooth communication instead. | Possible | Very High | HIGH
4 | Documentation
4.1 | Specification Verification Matrix | List of specifications that the finished product must pass. Used to inform our design decisions and prioritise importance of features. | 7 days | Kieran |  | Risk that we neglect to consider a specification necessary for the operation of the device. Very low impact if indeed the case. | Rare | Very Low | LOW
4.2 | SAGE, EIA, DMP forms | Completion of Sage Ethical Considerations form, Equality Impact Assessment, and Data Management Plan, to be used as appendices in short design brief submission | 7 days | Kieran, Mark, Jordan |  | Risk that completion of forms brings up issues with regards to ethics, equality, or data management. Minimise risk by designing project in such a way as to avoid such problems. | Rare | Very Low | LOW
4.3 | Risk Assessment Matrix | Listing of tasks, and identification of key risks involved with each task using a risk assessment matrix | 7 days | Mark |  | Subjective assessment of risk occurrence likelihood and potential severity of outcome may be incorrect, leading to failure to implement sufficient measures to mitigate risks. Minimise risk by reassessing risks throughout project, and taking action as needed. Make sure to communicate risks effectively. | Rare | Low | LOW

## Risk Assessment Matrix
Highly Probable | 5 | 10 | 15 | 20 | 25
81-100% | Moderate | Major | Major | Severe | Severe
Probable | 4 | 8 | 12 | 16 | 20
61-80% | Moderate | Moderate | Major | Major | Severe
Possible | 3 | 6 | 9 | 12 | 15
41-60% | Minor | Moderate | Moderate | Major | Major
Unlikely | 2 | 4 | 6 | 8 | 10
21-40% | Minor | Moderate | Moderate | Moderate | Major
Rare | 1 | 2 | 3 | 4 | 5
1-20% | Minor | Minor | Minor | Moderate | Moderate
| Very | Low | Medium | High | Very High